## Sheet1
Sl.No | Component | Description | Days | Comments
1 | App setup | Analyse and app setup | 0.5
2 | Database | Domain Model design | 0.5
3 | Role Management | Create Project level and Module level roles | 0.5 | Admininstrator - With all r/w DocumentAdmin - With limited r/w ViewOnly - with read only
4 | File Explorer page | Directory Structure - Treeview | 3.5
|  | Displaying List of directories in treeview |  | Maintain selected forlder state in that session
|  | Create directory in treeview |  | Allow the Administrator and DocumentAdmin to create Directory
|  | Update directory in treeview |  | Allow the Administrator and DocumentAdmin to rename Directory
|  | Delete directory in treeview |  | Allow the Administrator and DocumentAdmin to delete Directory
Directory detail - Grid
|  | Displaying List of files in the selecgted directory of treeview | 12 | Display the metadata information like name, type, date modified and each row contains 3 action buttions for View,Edit, Delete
Add new file into selected directory of treeview
Viewing the selected file
Delete selected file
5 | Edit Document | Edit document page
|  | Show Revision history | 10 | Display the revision history in a taular format. And also provide Show revision action button.
|  | Show selected revision |  | Show the selected revision in readonly
|  | New revision functionality |  | Display the metadata information in a form and allow the user to edit Name of the document
6 | Access Rules | Manage Access Rules
|  | Show the List of Access rules in a table | 10 | Display the list in a table. Inherit the parent folder access rules and show them in read only. And show an action button for creating new access rule. Each row contains one action buttons for delete. And also have two action buttons at the bottom for "Cancel" and Apply Changes"
|  | Create new Access rule |  | On click of New rule button add a row to the table.
Update Access rule on Directory
Delete Access rule on Directory
7 |  | Unit Testing | 3
8 |  | Performance testing | 1
9 |  | Documentation and Publish to Market place | 2 |  | Hours/per day |  |  | Sprints
|  |  | 43 |  | 8 | 344 | 8.6 | 4.5