## Implemented Component
Sno | Title | Description | Mendix Version used | Implemented By | Team Lead | Status | Documentation | Code base location | Effort (in PD) | Start Date | End Date | Mendix Marketplace feasibility | Comment | Time Required for demo
1 | User Mangement | Importing Users assigning userrole + Exporting User import template + Overview + Create, Update, Delete users (Together with security roles) | 9.12.4 | Raghvendra Goud & Shweta Kadam | Hemagiri | Demonstrated | Documentation For User Management.docx | UserManagement | 8 Days | 2023-04-03 | 2023-04-14 | Yes | proper error handling for invalid roles, email…., ¦ Error free + Generic
2 | Exit indent | while leaving page by refresh, closing tab, closing browser¦A widget use to exist earlier but that doesn't works now so Creating custom Exit Intent |  | Sanjay Adwani | Dhanushant | Completed | Exit intent_Resuable component.docx | Exit Intent | 3 Days | 2023-04-13 | 2023-04-17 | No | "window.onBeforeUnload" javascript Function could be use to generate same result as of our snippet so removing it from feasible components | 5mins
3 | Deeplink File Download | We often need to send email with attachments , so Check if we can download File by using a deeplink + also check if the file can be downloaded as well without login ? Can this be used by multiple users |  | Dhanushant | Dhanushant | Demonstrated | Deeplink file download.docx | Deeplink_FileDownload.mpk | 2 Days | 2023-04-13 | 2023-04-14 | Yes |  | 5mins
4 | Delegation Module | User can assign another user as a delegate when he will be leave and manage all delegation access. Delegate user can login in original person account by given link. Admin can audit changes done by delegate user |  | Nalindas Chaurasiya | Achal | Ready to present | ReusableDelegation_helper.docx | ReusableDelegation_Helper.mpk | 5 Days | 2023-03-15 | 2023-03-21 | Yes |  | 15mins
5 | Webhook | Integrating webhook into mendix aaplications |  | Shivam choubey, Sanjay Adwani, Sonu Kumar | Dhanushant | Demonstrated | Webhooks.docx | Webhook Integration.mpk | 3 Days | 2023-04-03 | 2023-04-05 | No
6 | Login via Social media | Login via social media credientials in your application so that users don’t have to remember differnet passwords for different apps |  | Neetika Agarwal | Dhanushant | Demonstrated | Social media login | SSOLoginApp.mpk | 5 Days | 2023-03-27 | 2023-03-31 | No
7 | Multiple File download | In a microflow we can't generate the report using either by using SAME Entity or Same Template so Need poc on how we can download multiple files |  | Vipul Maurya | Dhanushant | Demonstrated | POC_MultiDocument.docx | POC_MultipleFileDownloads | 4 Days | 2023-04-03 | 2023-04-06 | No
8 | Workflows | Exploring Marketplace widgets for workflows and R n D in general of workflows |  | Sonu kumar, Anusha sinha | Dhanushant | demonstrated | Workflows.docx |  | 8 Days | 2023-04-06 | 2023-04-17 | No
9 | Native apps | Basic Functionality EveryOne worked but Need to ExpolerMore on Native Mobile, Explored some things but native app is not running(VIEW) in our systems we tried every possible config. so was not able to explore Much on this |  | Sonu kumar, Shivam Choubey | Dhanushant | Completed | Native apps read me.docx |  | 4 Days | 2023-04-05 | 2023-04-10 | No
10 | Save the view of the datagrid on Browser | We can hide or show the columns on eye icon in data grid 2 , if we refresh the page data grid 2 will show default column only | 9.24.0 | Shubham & Shraddha Gupta | Disha | Demonstrated | https://nagarro.sharepoint.com/:f:/s/MendixReusableComponent/Ev4oB1qGc3pApM3936IpRfkB4Dk-DlBRq-AAYRWnGk2h-Q?e=m51iFD | https://nagarro.sharepoint.com/sites/LowcodePractice-Mendixplatform/Shared%20Documents/Forms/AllItems.aspx?ga=1&OR=Teams%2DHL&CT=1681904323068&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyNy8yMzAzMDUwMTExMCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&id=%2Fsites%2FLowcodePractice%2DMendixplatform%2FShared%20Documents%2FMendix%20platform%2FMPK%5FPOC%5FFiles%2FStore%20or%20save%20data%20grid2%20views%20on%20browser&viewid=1c389eea%2Df074%2D480b%2Da03d%2D15c35b9cc02c | 3 Days | 2023-04-03 | 2023-04-05 | No
11 | Gramatical plugin | To create an Input text area for gramatical syntax and spelling checks along with word/sentence suggestions - Specially useful for applications that allows email writing. | 9.18.0 | Sumit | Shraddha N | Ready to present | GrammarlyPlugin.mpk.zip | TBU |  |  |  | Yes | Widget is created, needs some work to be published to Marketplace
12 | Automated Testing | Unit Test module from Market place & create a new module out of it with additional example that can give more in-sights about unit testing This module can be used as good reference in case if any project suppose to do automated unit testing (Using Mendix capabilities) |  | Surbhi Agarwal & Raj Kumar | Hemagiri | Demonstrated | Automated Testing.docx | AutomatedTesting.mpk | 3 | 2023-04-03 | 2023-04-06 | No
13 | Natigate to Input which was having invalid input | when we have a form with so many fields and submit button is at the bottom, when any validation fails, we did not get any info about at which text box or input item that validation fails. | 9.24.1 | Bhanu | Bhanu | Demonstrated | Validation |  |  |  |  | No | Will not be placed on marketplace but can be used internally by the team if required. | 10 min
14 | Teams Integration | MS Teams Integration with Mendix App. which gives the ability to have a normal chat with the user. similer to what we are doing on MS. Teams Platform. | 9.18.4 | Praveen Kumar | Disha | Completed | TeamsIntegration_POC |  |  |  |  | No | No need for demonstration
15 | Dynamic Breadcrumbs | Mendix provides us building blocks for Breadcrumbs.However, they are static and hence we tried and implemented Dynamic breadcrumbs using nanoflow | 9.18.4 | Aakansha Sirohi | Bhanu | Demonstrated | Dynamic Breadcrumbs |  |  |  |  | No | Need project specific configuration so rather to push marketplace we can use that internally if needed. | 10 min
16 | Password Protected PDF | We can secure our pdf document with any desired password.We implemented this using a java action in which we pass 2 parameters -Pdf document(object) and password(string) | 9.18.4 | Aakansha Sirohi | Bhanu | Demonstrated | PasswordProtectedPDF |  |  |  |  | Yes | Java action can be publish to marketplace. | 10 mins
17 | Country State Master data | Build a module for country master data, so that developers can directly import that module and they can have all the master data regarding countries & their respective states. | 9.1.1 | Bhanu Chauhan | Bhanu | Demonstrated | Country State Master data Module |  |  |  |  | Yes | We can publish this module to marketplace. | 10 mins
18 | Dynamic table | This module enable us to create tables where both the number of rows and columns are dynamic | 9.18,4 | Sakshi Gaur | Disha | Demonstrated | Dynamic Table | DynamicTable.mpk |  |  |  | Yes
19 | Bulk Data Excel Export | Exporting to excel 100000 recored got exception that memory overflow- can use delemeter and create different excel | 9.18.4 | Praveen Kumar | Disha | Demonstrated | Bulk Data Excel Export |  |  |  |  | No | We can use it internally.
20 | Hide Excel | This widget will take input from user and then hide the excel sheets as per user inputs. Java action will take sheets as input and then hide them. | 9.12.4 | Raj Kumar | Hemagiri | Demonstrated | Hide Excel Sheet.docx |  |  |  |  | Yes | We can publish this Java library to marketplace.
21 | New String Functions | This module adds a number of reuable javascript actions for implementing additional string functions which are currently not available in Mendix. | 9.18.0 | Radhika Tapdiya | Disha | Demonstrated | String Functions Enhancement |  |  |  |  | yes | Javascript action can be publish to marketplace.
22 | Counting Days | This module finds and displays the Number of Days and occurences of Days (Mon, Tue, Wed etc.) between two dates selected by user | 9.18.0 | Nachiket Lonkar | Shraddha N | Demonstrated | Counting of Days |  |  |  |  | Yes | Module can be published to marketplace
23 | Image Conversion | This module can be used in Mendix apps to perform various conversion operations on images based on the different java actions. The module contains the four custom java actions which help users to convert, resize as well as add watermarks on the images. | 9.18.0 | Atharav Waghmare | Singham Babu | Demonstrated | Image Conversion based on selected option |  |  |  |  | Yes
24 | Expand and Collapse All | This Pluggable Widget can be used to Implement the Expand/Collapse All Accordions, by Clicking on expand all button it will expands all the accordions and vice versa and we can change those buttons label via selecting any options (Like Label, Icons or even Both) form the dropdown as per required. | 9.18.0 | Saikiran Kasam | Singham Babu | Demonstrated | Expand and Collapse All Accordion |  |  |  |  | Yes
25 | Collapse Expand | This Pluggable Widget can be used to implement Collapse/Expand Button for All Group Boxes . This widget contains two buttons Collapse and Expand .We can collapse all the Group Boxes by clicking on Collapse Button and expand all the Group Boxes by clicking on Expand Button. | 9.12.4 | Kamini Shrivastava | Singham Babu | Demonstrated | Collapse Expand All Group Boxes |  |  |  |  | Yes
26 | Expand and Collapse All | This Pluggable Widget can be used in Implementing the Expand/Collapse All for the Tree created using treeview widget. This widget contains two buttons Expand All and Collapse All on clicking calls the custom Js code and expands all the Trees and collapses all the Trees. | 9.19.0 | Maragoni Sai Praneeth | Singham Babu | Demonstrated | Expand and Collapse All in Treeview |  |  |  |  | yes
27 | Customized Chart using JS | Widget that provides interaction of the charts with the users of the app, With this widget, we can send data back and forth to your mendix app and vice-a-versa | 9.18.4 | Bhanu Gaur | Hemagiri | Demonstrated | Customized Chart JS |  |  |  |  | Yes | Developed as a part of SMO project

## In progress components
Name | Description | Idea by | Status | Effort Estimation | Picked by | Feasbility analysis Doc url | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Code Base url | status |  | Team
Whatsapp integration | from application send and receive messges to whatsapp | Achal | Already existing |  | Anusha Sinha | [6 empty] | Already existing | Twello connector
Outlook integration |  | Achal | Already existing |  | Sonu Kumar | [6 empty] | Already existing | Creating Outlook Meetings from your Mendix app ¦ by Hari haran ¦ Mendix Community ¦ Medium
Imap receive mail in mendix | via mendix we can send Mail to outlook and once the user replies on Outlook we should also Get that mail in Mendix | Achal | Already existing |  | Dhanushant | [7 empty] | Office Plugin ¦Email Connector ¦ IMAP/POP3 Incoming email
2 different application communication between | Microservices arcitecture ¦Very few people knows this ¦ how it work need POC on this | Achal | Not feasible
Connectors POC | there are various connectors in the marketplace we need to explore more so that at time of development we can utilize time | Achal | Not feasible
Native app POC | Various things available in Native apps ¦ POC required for better explore | Achal | Not feasible
JAVA action to save,cancel, Close,delete Action button | Default save button saves parent and all hirerachy elements but it should inform the user as well for this before action, also user should decide for all commit or only parent commit | Gouranga | In Progress | 10 days | Shubham Garg | Not Required as already implemented in previous project | 2023-05-03 | 17/05/2023 | 2023-05-03 |  |  |  |  | Shubham
MindMap ¦Mermaid | There is one of good use case for mindmap. Which will help to the client to pictorial data in MindMap journey. Please consider this as a reusable component. It will be very helpful for every client. Siemens has already created a custom component but that is not supporting mind map and they are not doing more new update. I would request to create this custom component. | Achal | Not feasible | 10 days | Prashanth | Feasiblity analysis Mermaid Updated Version.docx | 2023-04-26 | 2023-05-05 | 2023-04-26 |  |  |  | 2023-04-25
Wijmo grid | Wijmo Grid is a speacialty grid similar to data grid but with enhanced functionality, mainly: one to mant relation tree node like display with a grid and CRUD operations. | Shubham garg | Parked for later | 20 days | Shraddha Gupta | https://nagarro-my.sharepoint.com/:w:/p/shraddha_gupta/EfiA-Q21iqBJh2UWG_xLbfsB8rsPxnNYVBQdSkkPUiUdGQ?e=UlQ3WP | 2023-04-19 | 2023-05-26 | 2023-04-19 |  |  |  | React reusable component | Shubham
Collapse all, Expand all Buttons for Group Boxes | By clicking on expand all button, all the group boxes state should change to expanded. By clicking on collapse all button, all the group boxes state should changes to collpased. | Singam Babu | In Progress | 8 days | Kamini | https://nagarro.sharepoint.com/:w:/r/sites/MendixReusableComponent/_layouts/15/Doc.aspx?action=edit&sourcedoc=%7B7f605553-7b6c-4f7f-b243-d509355d17dc%7D&wdOrigin=TEAMS-ELECTRON.teamsSdk.openFilePreview&wdExp=TEAMS-CONTROL&web=1 | 2023-04-19 | 2023-04-28 | 2023-04-19
Collapse all, Expand all Buttons for Accordions | By clicking on expand all button, all the Accordion state should change to expanded. By clicking on collapse all button, all the Accordion state should changes to collpased. | Singam Babu | In Progress | 10days | Saikiran | Feasibility Report for Collapse and Expand All Accordion.docx | 19/4/2023 | 2023-02-05 | 19/4/2023
Collapse all, Expand all Buttons for Tree View | By clicking on expand all button, all the Treeview state should change to expanded. By clicking on collapse all button, all the Treeview state should changes to collpased. | Singam Babu | In Progress | 10 days | Praneeth | https://nagarro.sharepoint.com/:w:/s/MendixReusableComponent/Ee9gv3B1SI5Bj5Th7Ex3wicBSy0S5ekX4YJBEvN3qE1OSg?e=DsggPf | 19/04/23 | 2023-02-05 | 19/04/23
Toast bar/ Snack bar | Built using Microflow timer | Suddhapalli Sharvani | Already existing | Sanjay checking its feasiblity | Sanjay | [6 empty] | https://marketplace.mendix.com/link/component/111533
Multiple extension data to be merged into single PDF | POC | Sarath | Already existing |  | Sonu Kumar | [6 empty] | Mendix Marketplace - Cloudmersive API Suite
Custom Text Box | For integer attributes text box validation "Invalid Number" is blocking to all other events on the page/form, a custom text box based on mendix text box is a good idea. | Shubham garg | In Progress | 20 days | Aravind | https://nagarro-my.sharepoint.com/:w:/p/sontena_aravind/EYVnFX5EimtMugXmPn75XuUBwcxwFUfPeTgPo4BgGvg_1w?e=F87Uog | 25/04/23 | 2023-11-05 | 2023-05-03
Adding dynamic attributes from UI | Give the user the ability to add attributes on runtime. | Dhanushant | Not feasible |  | Vipul
Entity model as datasource for any charts | Use entities are source for charts instead of JSON | Shraddha Naik | In Progress | 20 days | Rajesh
OQL to Excel |  | Shraddha Naik | In Progress | 10 days | Shraddha N | https://nagarro-my.sharepoint.com/:w:/r/personal/shraddha_naik_nagarro_com/_layouts/15/Doc.aspx?sourcedoc=%7B36fd65f3-cfe0-442b-ba78-8960d3c39a86%7D&action=editnew&wdPreviousSession=1b0b0438-5c2b-4625-9d22-ca20cd9e44e9&wdNewAndOpenCt=1683265668441&wdo=4&wdOrigin=wacFileNew&wdTpl=blank&wdLcid=1033&wdPreviousCorrelation=1908ec11-54b3-4864-81a0-d88cadc96caf | 25/04/23
Face Recognition Auth | Give user ability to login to application via Face recognition authentication | Vipul Maurya | Already existing |  | Vipul | [7 empty] | Azure face API- https://marketplace.mendix.com/link/component/208288
Malicious File Scanner | To scan files which may contains Malwares | Vipul Maurya | Already existing |  | Vipul | [7 empty] | Some free third party APIs which can be use: https://geekflare.com/security-threats-detection-api/
Personal Email Signature |  | Vipul Maurya | Already existing |  | Nalindas
digital sign in pdf(Initally Unveriffied tick) | PDF are digitally signed and when they are downloaded they are they shows "validity unknown" or "Not verifed" and once validated they became validated or success | dhanushant | Not feasible | 4 days | Dhanushant |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 26-04-2023
Drop down of the CONTENT From one view to another |  | Shubham Vijayvargiya | Not feasible | 3 days | Shubham Vijayvargiya |  | 2023-04-24 | 26-04-2023 | 2023-04-24 | 26-04-2023
Starter App | Starter App will contain all the required modules that are reused in almost every app development. Every time we create an app in mendix the developer has to rework on implementing the same modules. To replace these reoccurring steps and to decrease time to development we will find an app that can be used as a starting pointrather than each time building from scratch. Such an app can also be used to give an initial mendix demo to new clients. | Surbhi Agarwal | In Progress | 4days | -> SSO - Raghuvendra -> Excel Import & Export - Nidhi Singh -> API Integration - Hammad -> Email - Shweta | Starter App Feasibility.docx | 2023-04-25 | 2023-04-28 | 25/04/2023
Context sensitive helper widget | This widgets help in displaying content based on the user's current location in the application. | Sonu | Not feasible | 3days | Sonu
Time zone conversion widget | It allows users to convert times and dates to different time zones. | Sonu | Already existing | 3days | Shivam
Reading of text from Images | Reading Text from an uploaded image or the image which is Already existing in mendix db and return extracted string. | Aravind | Already existing |  | Aravind
Excel export - Show or hide sheets with only one template creation | This widget will take input from user and then hide the excel sheets as per user inputs. Java action will take sheets as input and then show hide them. | Seerapu Hemagiri | In Progress | 5 days | Raj Kumar | ShowHide Excel coulms Feasibility.docx | 2023-04-27 | 2023-05-03
Employee time tracking system | It helps in employers monitor and record the hours worked by their employees, usually through a digital platform. | Sonu | Not feasible | 2days | Anusha
KYC verification process using Aadhaar card | Need to be developed new widget or module to verify user KYC document with Aadhaar number + OTP using Aadhaar API. Biometric verification out of scope. | Gouranga | Not feasible | 7 days | Bhanu | KYC Using Aadhar Card-Feasibility.docx | 27-04-2023 | 2023-05-05
Watermarking service | Adding watermarks to Documents | Shraddha Naik | Already existing
Customization of Rating service |  | Shraddha Naik | Already existing
DataGrid 2 Export by default column & DataGrid 2 Export file doesn't export filtered data |  | Sakshi Gaur | Not feasible |  | Radhika Tapdiya | [8 empty] | Shubham
Unique list genaration module |  | Nachiket Lonkar | In Progress | 7 Days | Nachiket Lonkar |  | 2023-02-05 | 2023-11-05 | 2023-02-05
Social Media Share | Sharing mendix app content on any social media platform. | Shraddha Naik | In Progress | 20 days | Asha Maity | Social media widget.docx (sharepoint.com) | 25/04/23 | 23/05/2023
Social Media Commenting | Adding comments to open pages of organizations, which need no login | Shraddha Naik | In Progress |  | Shraddha N |  | 15/5/2023
SEO with mendix | how + where we should write the meta text so that we can optimize the search engine optimization for mendix apps | Dhanushant | Already existing | 3days | Nalindas |  | 2023-05-01 | 2023-05-03 | 2023-05-01 | 2023-05-05
Notify about Skipped/ Delayed Scheduled microflows | Skipped/ Delayed Scheduled microflows should be notififed | Dhanushant | Not feasible | 4days |  |  | 2023-05-01 | 2023-05-04 | 2023-05-01 | 2023-05-08
Storing Individual component interactions | Certain part of websites is usually highly interacted by the users so if we can calculates those interactions , The better it is , better new users it can add and will retain more users | Dhanushant | Already existing | 3 days | Dhanushant |  | 2023-05-01 | 2023-05-03 | 2023-05-01 | 2023-05-03
Portal Module | A Portal will act as a lobby for number of applications in such a way that user can redirect to any application whch is associated with the Portal | Vipul Maurya | Already existing | 2days | Vipul |  | 2023-05-01 | 2023-05-02 | 2023-05-01 | 2023-05-02
Maintenance mode | A module to help the administrators to work on some administrative tasks. During this activity no user except allowed administrator should not be able to access the application. And also there will be some notification shown to any user in landing page till the maintenance completed. Maintenance time and notification text, administrator uses allowed to login are cofigurable. | Sarath Chandra Babu Singam | In Progress
Digilocker Integration | DigiLocker aims to provide a Digital wallet to every citizen so that all lifelong documents anywhere anytime including Educational, Identity, health records. | Sarath Chandra Babu Singam | In Progress | 8 days | Aakanksha Sirohi | DigiLocker Integration.docx | 2023-05-08 | 2023-05-17 | 2023-05-08
Integeration with Telegram | This API allows you to build your own customized Telegram clients. | Sarath Chandra Babu Singam | Not feasible | 10 days | Jyoti Ahuja | Telegram Integration.docx | 2023-05-09 | 2023-05-22
Telegram Payments API | To accept payments from Telegram users around the world | Sarath Chandra Babu Singam | Not feasible | 3 days | Jyoti Ahuja | Telegram Payment Integration.docx | 2023-05-23
OTPLess login connector | OTPless login via whats app just paasing code to OTPless server. https://otpless.com/ | Achal Singh Rathore | In Progress | 7 days | Bhanu | OTPLess login connector.docx | 2023-05-10 | 2023-05-18
Browser Events | Widget in react to capture window events in browser (Reload, Back button, Close, Home button) | Seerapu Hemagiri | Already existing |  |  | check exit intent before starting: https://nagarro.sharepoint.com/:f:/s/LowcodePractice-Mendixplatform/Er9iqVTq4-JEqYtCZ88mTTYBLsu8svBq0C8qyKMpvki7eQ?e=Y100AI
Calendar Widget | Calendar widget using React | Seerapu Hemagiri | In Progress |  | Raghvendra Goud
Excel Export (XLS Module from Market Place) | Excel export () - Generate based on DataGrid2 personalization - This is extension to existing module in Market Place | Seerapu Hemagiri | In Progress |  | Raj Kumar
Twilio Whatsapp Messaging | Sending WhatsApp messages with Twilio Programmable Messaging globally with the Twilio API for WhatsApp​ directly in your Mendix application | Shubham Garg | Already Existing | 2days | Radhika Tapdiya |  | 2023-05-05 | 2023-05-08 | 2023-05-08 |  |  |  |  | Shubham
React mention's widget in mendix | In comment type of fields user will be able to mention the specific person by @ symbol, like JIRA | Shraddha Gupta | In Progress | 12 days | Shailja Patel | React Mention Widget in mendix.docx | 2023-08-05 | 26/05/2023 | 2023-11-05 |  |  |  |  | Shubham
Enumeration Dropdown with search feature | In dropdown it is better to have a search field to search the values | Shraddha Gupta | In Progress | 10days | Shraddha Gupta | https://nagarro-my.sharepoint.com/:w:/p/shraddha_gupta/Ec0WUO-dBSJGiuXBGd8kRHMBAoTmr3FFEIGe127zQjxlag?e=WO5aoK | 2023-12-05 | 30/05/2023 | 2023-12-05 |  |  |  |  | Shubham
Additional String Functions for Mendix | Adding few more string functions in Mendix which can be used by calling Java Action | Radhika Tapdiya | In Progress | 2 days | Radhika Tapdiya |  | 22/05/2023 | 25/05/2023 | [5 empty] | Shubham
Data grid2 row selection | row Selections are are getting cleared when we go to next page using pagination in datagrid2 | Shubham Vujayvargiya | In Progress | 3 days | Sakshi Gaur |  | 25/05/23 | 29/05/23
Chatbot/ Q&A in mendix |  | Sakshi Gaur | Already existing | Feasibility check | Sakshi Gaur
Duplicate Jar files | A java action that identify duplicate jar files of different versions and remove older version files if possible | Sakshi Gaur | Not feasible | 3 days | Prashanth
Log out from application | log out from application if we close the browser tab | Sanjay Adwani | Already exist |  | Sonu/Sanjay |  | 2022-05-26
Text file generation | Generate txt file in microflow | Sanjay Adwani | Already existing |  | Sanjay Adwani
Conditional visibility for columns in datagrid 2 | Add condition visibility in column | Shivam choubey | In Progress | Feasibility check | shivam choubey | [8 empty] | Disha
Add dynamic content to popup menu | Currently we have mendix marketplace widget with popup menu name, but we are able to only provide static content not dynamic in it. It's not abailable in mendix It was an actual project reruirement. | Shubham Vijayvargiya | In Progress | Feasibility check | Vipul Maurya
Utilize any npm package for small functionalities | For some of the functionality, we can use npm packages in our JS code as an utility. It can help in migration projects where we have some code already available | Shubham Vijayvargiya | In Progress |  | Shubham Vijayvargiya
Drag and drop widget POC | Drag and drop items from one view to another. Widget is already available, but this will be an good example with requirement usage. | Shubham Vijayvargiya | In Progress |  | Shubham Vijayvargiya
Concept : Toastr implementation with real time user update is multiple users are working on same thing | If 2 users are working on same field and one user click on save, another user will be updated with saved data and get a toastr message | Shubham Vijayvargiya | Already Existing | Feasibility check | Jyoti Ahuja | This is a kind of concept of locking a particular record while editing it, which can easily be achieved using various approaches respective to the client requirement and there is nothing which we cannot perform to have this functionality hence concluded it as already existing.
Mathematical calculation in mendix |  | Radhika Tapdiya | Already existing | Feasibility check | Praveen Kumar | https://marketplace.mendix.com/link/component/112522 | 24/05/2023 |  | 24/05/2023 | 24/05/2023
Remove search string button on Text filter Datagrid 2 |  | Praveen | In Progress | Feasibility check + 4 Days | Praveen |  | 26/05/2023 | 2023-02-06 | 29/05/2023
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Disha Sharma please add description
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Dhanushant @Surbhi Agarwal @Neetika Agarwal @Prashanth S @Sumit Banerjee @Shraddha Naik @Singam Babu @Surbhi Agarwal @Shubham Garg @Bhanu Chauhan @Seerapu Hemagiri @Harshit Agarwal @Disha Sharma Please add effort estimation, due date, feasibility analysis doc link for each component
Note on G8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Shubham Garg please update
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Shubham Garg please update description
Note on E16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Shraddha Naik please update effort estimation
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not feasible with default architect of Mendix and security breach issue
Note on D36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Shraddha Naik pls update
Note on G52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Shraddha Gupta please update this

## Teams
Dhanushant | Shradha Naik/Sumit Banerjee | Seerapu Hemagiri/Surbhi Agarwal | Sarath Singham | Harshit/Bhanu Chauhan | Disha/Sakshi gaur
Sanjay Adwani | Nachiket Lonkar | Raghvendra Goud | Suddhapalli Sharvani | Aakanksha Sirohi | Praveen Kumar
Shivam Choubey | Rajesh Jha | Surbhi Agarwal | Atharav Girish Waghmare | Bhanu Chauhan | Radhika Tapdiya
Nalindas Chaurasiya | Asha Maity | Hammad Ahmed | Maragoni Sai Praneeth | Jyoti Ahuja | Sakshi gaur
Sonu Kumar | Madhusudanarao Avvaru | Shweta Nandakumar Kadam | SaiKiran Kasam |  | Shailja Patel
Vipul Maurya | Sumit Banerjee | Nidhi Singh | Kamini Shrivastava |  | shraddha Gupta
Shubham Vijayvargiya | Sontena Aravind | Raj Kumar | Sumesh Arora
Anusha Sinha

## Mendix Certifications
Name | Email Id | Total Exp as on 1 Apr 23 | Relevant exp in Mendix as on 1 Apr 23 | Rapid Certification | Intermediate Certification | Advance Certification
Aakanksha Sirohi | aakanksha.sirohi@nagarro.com | 1.8 | 1.4 | yes | yes | Planning
Abhijeet Dhali | dhali.abhijeet@nagarro.com
Abhijeet Singh Rautela | abhijeet.rautela@nagarro.com
Achal Rathore | achal.rathore@nagarro.com
Aditya Swaroop | aditya.swaroop@nagarro.com
Amol Salunke | amol.salunke@nagarro.com
Anas Mateen | anas.mateen@nagarro.com
Ankit Gupta | ankit.gupta20@nagarro.com
Anshika Verma | anshika.verma@nagarro.com
Anusha Sinha | anusha.sinha@nagarro.com | 5.5 | 2 | Yes | Yes | Yes
Asha Maity | asha.maity@nagarro.com | 1.2 | 0.8 | Yes | Yes | Planning
Ashish Kumar | ashish.kumar11@nagarro.com
Atharav Girish Waghmare | atharav.waghmare@nagarro.com | 2.4 | 2.4 | Yes | Yes | Planning
Bhanu Gaur | bhanu.gaur@nagarro.com
Bhanu Pratap Singh Chauhan | bhanu.chauhan@nagarro.com | 3.3 | 2.7 | Yes | Yes | Yes
Chandan Kumar Sahni | chandan.sahni@nagarro.com
Dhanushant . | dhanushant@nagarro.com | 2.7 | 2.1 | Yes | Yes | Yes
Disha Sharma | disha.sharma01@nagarro.com | 7.7 | 2.1 | Yes | Yes | Planning
Govindan G | govindan.g@nagarro.com
Hammad Ahmed | hammad.ahmed@nagarro.com
Harishankar Nair | harishankar.nair@nagarro.com
Harshit Agarwal | harshit.agarwal@nagarro.com
Himanshi | himanshi01@nagarro.com
Ishant Kushwaha | ishant.kushwaha@nagarro.com
Ishwari Paranjape | ishwari.paranjape@nagarro.com
Jyoti Gupta | jyoti.ahuja@nagarro.com/jyoti.gupta02@nagarro.com | 11 | 0.8 | yes | yes | planing
Lalit Singh | lalit.singh01@nagarro.com
Madhuchetan B | Madhuchetan B
Madhusudanarao Avvaru | madhusudanarao.avvaru@nagarro.com | 3.3 | 2 | Yes | Yes | Planning
Maragoni Sai Praneeth | maragoni.praneeth@nagarro.com | 0.4 | 0.4 | Yes | planning
Meenal Jain | meenal.jain@nagarro.com
Mogal Begum | mogal.begum@nagarro.com
Mohammed Salar | mohammed.salar@nagarro.com
Nachiket Lonkar | nachiket.lonkar@nagarro.com
Nalindas Chaurasiya | nalindas.chaurasiya@nagarro.com | 2.8 | 2.8 | Yes | Yes | Yes
Neetika Agarwal | neetika.agarwal@nagarro.com | 5.7 | 2.2 | Yes | Yes | Yes
Nidhi Singh | nidhi.singh03@nagarro.com | 0.4 | 0.4 | yes | planning
Prashanth Kumar S | prashanth.s@nagarro.com | 6.9 | 3.9 | Yes | Yes | Planning
Praveen Kumar | praveen.kumar07@nagarro.com | 2.6 | 0.9 | Yes | Yes | Planning
Preeti Dangi | preeti.dangi@nagarro.com
Pritam Kumar Das | pritam.das@nagarro.com
Radhika S Tapdiya | radhika.tapdiya@nagarro.com | 7.5 | 1.1 | Yes | Planning
Raghvendra Goud | raghvendra.goud@nagarro.com
Raj Kumar | raj.kumar04@nagarro.com | 0.4 | 0.4 | yes | planning | Planning
Rajesh Jha | rajesh.jha@nagarro.com | 0.4 | 0.4 | Yes | planning
Rakhi Gupta | rakhi.gupta@nagarro.com
SaiKiran Kasam | saikiran.kasam@nagarro.com | 0.4 | 0.4 | Yes | planning
Sakshi Gaur | sakshi.gaur@nagarro.com | 3.3 | 2.7 | Yes | Yes | planning
Sanjay Adwani | sanjay.adwani@nagarro.com | 1.2 | 0.8 | yes | Planning
Sarath Singham | singam.babu@nagarro.com
Seerapu Hemagiri | seerapu.hemagiri@nagarro.com
Shailja Patel | shailja.patel@nagarro.com | 1.2 | 0.8 | Yes | Yes | Planning
Shivam Choubey | shivam.choubey@nagarro.com | 1.2 | 0.8 | Yes | Yes | Planning
Shraddha Gupta | shraddha.gupta@nagarro.com | 1.8 | 0.9 | Yes | Yes | Planning
Shraddha Naik | shraddha.naik@nagarro.com
Shubham Garg | shubham.garg07@nagarro.com | 3 | 2
Shubham Vijayvargiya | shubham.vijayvargiya@nagarro.com
Shweta Nandkumar Kadam | shweta.kadam@nagarro.com | 0.8 | 0.5 | Yes | Planning | Planning
Sontena Amruth Aravind | sontena.aravind@nagarro.com | 2.2 | 1.8 | yes | yes | Planning
Sonu Kumar | sonu.kumar02@nagarro.com | 1.2 | 0.8 | yes | yes | Planning
Spica Rawat | spica.rawat@nagarro.com
Sudarshan Kumar | sudarshan.kumar@nagarro.com
Suddhapalli Sharvani | suddhapalli.sharvani@nagarro.com | 4.5 | 3 | Yes | Yes | Yes
Sumesh Arora | sumesh.arora@nagarro.com | 4.8 | 3 | Yes | Yes | Planning
Sumit Banerjee | sumit.banerjee@nagarro.com | 5.6 | 2 | Yes | Yes | Yes
Surbhi Agarwal | surbhi.agarwal01@nagarro.com | 4.9 | 3.5 | Yes | Yes | Yes
Vijaylakshmi Tomar | vijaylakshmi.tomar@nagarro.com
Vikas Bhalla | vikas.bhalla@nagarro.com
Vipul Maurya | vipul.maurya@nagarro.com | 1.11 | 1.9 | Yes | Yes | Planning
Vishal Kadam | vishal-janarath.kadam@nagarro.com | 2.2 | 2 | Yes | Yes | Yes
Kamini Shrivastava | kamini.shrivastava@nagarro.com | 1.8 | 0.3 | Yes | Yes