## Sheet1
SrNo | Component | Discription | Comments | Hours
1 | Application setup | Application setup and analyse |  | 4
2 | Database | Domain model design |  | 4
3 | Role Manageent | Module level and Project level roles | Adminsitrator- Full read/write (Can raise requests, import request data in bulk and submit request) User- Limited read/write (Can raise and submit own request) | 2
4 | Request overview page | Overview page with raise, edit, view and delete request functionality |  | 16
5 | Excel import and export | Admin can import request data in bulk, and export the submitted data in Excel. |  | 6
6 | Email configuration | Respective user will receive an email with QR code after submit of request |  | 8
7 | deeplink Configurations | Deeplink genreation for each request as a input string for QR code |  | 8
8 | QR code generation | Unique QR code will be generated in submission of each request |  | 6
9 | Application testing and deployment |  |  | 6
Effort in days
|  |  | Total estimtion | 60 | 7.5