## Sheet2
S.no | Component | Description | Estimate (in days) | Comments | Note: Component 1 needs to be completed before move to another module. As all components are dependent on first component. After completion of 1st component all other components can be devloped in parallel.
1 | Employee information | Personal info | 5 |  | 2 Devlopers can work on 1 component.
Employee designation
|  | Assign Location |  |  | Our primary concern revolves around reusability, considering the significant size of the module. We anticipate challenges in achieving a high level of generality, as each organization possesses its unique set of structures and tasks, potentially limiting widespread adoption.
Assign Technology
Employee reports to
Assign Team
2 | Employee Request | Employee can request additional services like changing of location , change of a team etc. | 4
Notify HR/admin when request created
Action taken on request
3 | Skills Report | Manage employee skills | 5
Skill Report for all employee
Technical skills
Quantitative
Qualitative
Languages
4 | Trainings | Schedule trainings | 5
Training reports
5 | Absence Management | Add absence | 6
Absence calendar
Absence report
6 | Job Application | Accept new job application | 4
Review job application
7 | Job Posting | HR will post the new jobs | 2
8 | HR Interviews | Manage interview | 4
Interview report
9 | Super Admin Functionality | Content Management | 2
|  | Excel import template for bulk data | 2
|  | Excel export template for bulk data | 2
|  | Email configuration | 1
|  | Dev Effort | 42
|  | Testing | 8.4
|  | Total | 50.4