## Tasks
Technical Tasks | Description | Status | Assignee
App Creation |  | Done | Shraddha
App Configuration |  | Done | Bhanu
Design Domain model |  | Done | Shraddha
Create Registration Form |  | Done
Nagarro theme |  | Done | Kamini
Email Configuration |  | Done | Praneeth
Create Email template to be shared with Vendors - Invitation Email |  | Done | Kamini
Role Configuration |  | Done | Sakshi
Approval email setup |  | Done | Kamini
Login for Vendor |  | Done | Bhanu
Deeplink Configuration |  | Done | Bhanu
User name and password creation for Vendor accounts |  | Done | Bhanu
KYP validations |  | Done | Bhanu
Send email on registration form submission |  | Done | Kamini
Multilingual support |  | Done | Praneeth
Approver Dashboard | List of Vendor Approval requests to be displayed | Done | Praneeth
Reminder for approval to approvers | 5 days reminder | Done | Kamini
Add username & pwd in vendor email | Username and pwd is vendors email id | Done | Kamini
Due date and email , non editable on Vendor Registration form |  | Done | Bhanu
Save as a draft option on Vendor Registration form |  | Done | Bhanu
The user needs to input name of document in case of 'Other' category |  | Done | Bhanu
Vendor overview page, Detailed page for each item in overview page |  | Done | Bhanu
List view for Initiator to see all registeration initiated by him |  | Done | Bhanu
Initiator can update the due date until status is incomplete |  | Done | Bhanu
Don't allow if duplicate registration initiated | Duplicate check to be added on email | Done | Bhanu
Document type should be mandatory | Instead of document name show the document type and if document type is other than show ask user to enter name for that document. | Done | Bhanu
Approval Flow | 1. 4 Tabs - My Tasks(requests pending with that approver) , Approved, Rejected, All Requests 2. Only Approvers can Approve or Reject the requests (admin has no access) 3. After Approving/Rejecting the request should not appear in My Tasks | Done | Praneeth
Admin Dashboard | A Dashboard that is visible to admin | Done | Praneeth
Flow Change Based on Designation | Accounts will be linked to a designation of a certain level | Done | Praneeth
Level Based Approvals | Approval Flow based on levels | Done | Praneeth
Accept and Reject flow of a vendor | Accept and Reject Microflows of a Vendor with respect to deignaton and level. Sequential Flow of Approval is done | Done | Praneeth
Fixed issues in Vendor Submit Flow and Approver Approve Flow | Fixed issues in Vendor Submit Flow and Approver Approve Flow | Done | Praneeth
Improved the Performance | Improved the Performance by implementing the suggested changes by Mx Assist | Done | Praneeth
Approval Flow for a Approver | Showing list of vendor approvals based on the level of the designation of the particular account | Done | Praneeth
Code and Folder through Best Practices | Created folders for Mendix Best Practices | Done | Kamini
Random Password Generator | Random Password Generator for Vendor After Initiation for Login | Done | Kamini
DeepLinks with Emails | Configure DeepLinks with all respective Email | Done | Kamini
Brand Configuration | Logo and Company Name can be dynamically change | Done | Kamini
Complince Check for PAN and CIN | Done CIN and PAN but PAN is Paid and took CIN from https://data.gov.in/catalog/company-master-data | Done | Praneeth
Compliance Check for GST and URN | Not getting free APIs, workflow has been implemented | Open | Kamini
Emails for Vendor accept and reject request | Email for Vendor accept and reject request based on conditions | Done | Kamini
New Status - Request for Information | Introduce new status for approvers to ask for additional information from vendors | Done | Praneeth
Send Email on requesting for information | Vendor should receive email when approver ask for additional information | Open | Praneeth
Request Tracking | The vendor should track the application status . | Open | Kamini
Audit Trail | Keep a track of changes in data. | Open | Kamini

## Queries
Queries
What happens if approver does not approve within the defined time or before due date?
No. of days required for approving a vendor request?
What happens if teh Vendor fails to register within the due date?
What happens if request reject by approvers?

## Use Cases
Supplier Onboarding | Registration page - Capture vendors information | SCM to generate an invite with the registration URL: - Supplier receives the email invitation and uses the URL - A registration form should be open where the required details should be captured. 1. Name 2. Contact information 3. Address.. Etc On successful registration a temp account to be created.
Supplier Onboarding | Registration page - Option to upload the documents | During the registration process a checklist of documents to be uploaded like PAN, GST certificate etc.
Supplier Onboarding | Vendor Registration submission | Generate a unique id for every successful registraion. The same can be shared as Application ID to the supplier. - Once the user submitted the form, an email notification should be sent to SCM team (or relavent person/team). - Also a acknowledgement mail for submitting the registration request should be sent to email used for registration process. - Status of application should set to "Application Submitted"
Supplier Onboarding | Create temp account | Application should ask user to create user id and password so that supplier can login and check the application status or update the information if requested by ABG NJ team.
Supplier Onboarding | Track application | User should be able to track the application status by login in with the user id he/she has created during registration. - Submitted - In Review - Request for information - Approved
Supplier Onboarding | Request for information | There should be an option for "Request Information", in case SCM/Finance team needs some more information then they can utilize this option. - Comments - comments should be mandatory to provide details about what information is needed. - Status of the application should be set to "Requested for information" - An email notification should be sent to the supplier with the comments provided by the team - Supplier should be able to update the form and re-submit it.
Supplier Onboarding | Supplier registration review - SCM Team | SCM to have a menu option as "Onboarding" where they can view all the new and in progress onboarding in a list view. - Details of the application can be viewed based on the application id - On Review the application can be approved, rejected, request for more information - If approved, the data is sent to finance team for further approval
Supplier Onboarding | Vendor registration approval - Finance Team | Similar to SCM the finance user access to "Onboarding" where they can view all the in progress onboarding request. - Email notification for the new approval request to the finance team - Details of the application can be viewed based on the application id - On Review the application can be approved, rejected, request for more information
Supplier Onboarding | Onboarding Request Rejection | The SCM or the Finance user can reject the onboarding request. - On Rejection the reasons are mandatory to be filled - The same reason should be sent in the email notification to the supplier - The Temp account should be disabled. - A regret email should be sent to the requestor
Supplier Onboarding | Supplier Creation | On approval of the Finance user the data of the supplier to be sent to M365 for supplier creation. In response the M365 to provide the Supplier ID which will conclude the onboarding process. In case registration got approved (by all the teams) then a welcome mail should be sent to the requestor

## Roles
Roles
Vendor
Initiater/Internal User
Admin
Approver1
Approver2